## Allocations
PROJECTS
ID | Title | Admin | UPC | SS Rd 6 ID | PE Start | RW Start | CN Start | CN End | PE Est | RW Est | CN Est | TOTAL Est | Other Funds | SYIP Funds | Non-SYIP Funds | FY21 | FY22 | FY23 | FY24 | Previous | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | Total CVTA | Balance to Complete | Notes
CVTA-0001 | #FLT - DB 2 - Chesterfield, Petersburg, Colonial Heights (Segments 1A - 2B) | VDOT | 121511 | [8 empty] | 72440000 | 42457388 | 42457388 |  |  | 25000000 |  |  | 25000000 | [7 empty] | 25000000 | 4982612 | Moved $25M from DB3 to DB2 per CVTA Action (Sept 2023)
CVTA-0002 | #FLT - DB 1 - Ashland, Hanover, Henrico (Segments 7.C2 - 7.C4) | VDOT | 121374, 119599 |  | FY23 | FY24 | FY25 |  | 175000 | 3017000 | 14268000 | 17459709 | 9078599 | 9078599 |  |  |  | 2459287 | 4741320 | 7200607 | FY25: 1180504 | 8381111 | -1
CVTA-0003 | C Commerce Road - FLT Phase II | Local |  |  | FY26 | FY29 | FY30 | FY32 | 5636774 | 5507873 | 65014334 | 76158981 | 0 | 0 | [5 empty] | 0 | FY26: 4767006; FY27: 8456857; FY30: 11434376; FY31: 13500000 | 38158239 | 38000742 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0004 | #FLT - C Commerce Road - Phase I | Local | 118946 |  |  | FY25 | FY26 |  | 1391127 | 984860 | 10065472 | 12441459 | 9441459 | 9441459 |  |  |  |  | 1391127 | 1391127 | FY26: 984860; FY27: 624013 | 3000000 | 0
CVTA-0005 | #FLT - DB3? - Chesterfield (Segments 2C - 3A) | [10 empty] | 0 | 0 |  |  |  | 194503 |  |  | 194503 | [7 empty] | 194503 | -194503 | Moved $25M from DB3 to DB2 per CVTA Action (Sept 2023)
CVTA-0006 | #FLT - Manchester Bridge (Segment 4E-R) | [7 empty] | 2637000 | 0 | 31370461 | 34007461 | 0 |  |  | 1500000 |  |  |  | 1500000 | [7 empty] | 1500000 | 32507461
CVTA-0007 | #FLT - Bryan Park (Segment 6B) | Local |  |  | FY24 |  | FY24 | FY25 |  |  |  | 3760000 | 0 |  |  | 3000000 |  |  |  | 3000000 | [7 empty] | 3000000 | 760000
CVTA-0008 | #FLT - Park St (Segment 6C) | Local | 117047 |  | FY22 | FY23 | FY24 | FY24 | 227000 | 78000 | 840000 | 890000 | 437000 | 210000 | 227000 | 713000 |  |  |  | 713000 | [7 empty] | 713000 | -260000
CVTA-0009 | #FLT - Lakeside Community Trail Ph 1 (Segment 6D.1) | Local | 118065 |  | FY22 | FY23 | FY25 | FY26 | 624000 | 118000 | 2270000 | 3310000 | 2560519 | 1982519 | 578000 | 396504 |  |  |  | 396504 | [7 empty] | 396504 | 352977
CVTA-0010 | #FLT - Lakeside Community Trail Ph 2 (Segment 6D.2) | Local | 118091 |  | FY22 | FY23 | FY25 | FY26 | 651000 | 98000 | 3450000 | 4290000 | 3363217 | 3363217 |  | 803000 |  |  |  | 803000 | [7 empty] | 803000 | 123783
CVTA-0011 | #FLT - Lakeside Community Trail Ph 3 (Segment 6D.3) | Local |  |  | FY22 | FY23 | FY24 | FY25 | 463000 | 200000 | 3536000 | 4150000 | 0 |  |  | 3073000 |  |  |  | 3073000 | [7 empty] | 3073000 | 1077000
CVTA-0012 | #FLT - Brook/Hilliard Road Diet (Segment 6E) | Local | 118153 |  | FY22 | FY24 | FY25 | FY26 | 597000 | 887000 | 4310000 | 6710000 | 4678000 | 4678000 |  | 1037401 |  |  |  | 1037401 | [7 empty] | 1037401 | 994599
CVTA-0013 | #FLT - Villa Park Phase (Segment 6G) | Local |  |  | FY22 | FY23 | FY24 | FY25 | 691000 | 560000 | 3146000 | 4890000 | 691000 |  | 691000 | 3706000 |  |  |  | 3706000 | [7 empty] | 3706000 | 493000
CVTA-0014 | #FLT - Longdale Trail (Segments 7A - 7C.1) | Local |  |  | FY22 | FY24 | FY25 | FY27 | 3186000 | 3621000 | 22470000 | 30390000 | 3186000 |  | 3186000 | 18791656 | 7299344 |  |  | 26091000 | [7 empty] | 26091000 | 1113000
CVTA-0015 | Capital Trail Crossings | [10 empty] | 234000 | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | 234000 | Project funded with non-CVTA funds; allocations removed
CVTA-0016 | I-64 at Ashland Rd (Rte 623) Interchange - DDI | VDOT | 123919 |  | FY26 | FY29 | FY30 | FY31 | 5374713 | 1274992 | 69268236 | 75917941 | 42218112 | 42218112 |  |  |  |  | 5314767 | 5314767 | FY27: 1895820; FY28: 26489242 | 33699829 | 0
CVTA-0017 | I-64 at Oilville Rd (Rte 617) Interchange |  | 123290 |  | FY25 | FY26 | FY28 | FY29 | 1346000 | 89000 | 6077512 | 7512512 | 4000000 | 4000000 | [5 empty] | 0 | FY28: 606000 | 606000 | 2906512
CVTA-0018 | Bottoms Bridge Park and Ride | VDOT | 120444 |  | FY22 |  | FY25 |  | 565766 | 0 | 3054497 | 3620263 | 3422216 | 3422216 | [5 empty] | 0 | FY25: 200000 | 200000 | -1953
CVTA-0019 | Stavemill Rd Turn Lane | [10 empty] | 1800000 | 0 |  |  | 1800000 |  |  |  | 1800000 | [7 empty] | 1800000 | 0
CVTA-0020 | Rte 288 NB Hard Shouder Running | VDOT | 122147 |  | FY24 | FY27 | FY28 | FY30 | 4839454 | 935413 | 33786868 | 39561735 | 31561735 | 31561735 | [5 empty] | 0 | FY28: 8000000 | 8000000 | 0
CVTA-0021 | GreenCity Connector Trail and Bridge | [7 empty] | 1655000 | 1960000 | 6363000 | 9978000 | 0 |  |  |  | 1655000 | 1960000 |  | 3615000 | FY25: 3181500; FY26: 3181500 | 9978000 | 0
CVTA-0022 | F Manchester Connection to James River | [7 empty] | 564900 | 1034997 | 4744934 | 6344831 | 0 |  |  |  |  | 564900 | 1034997 | 1599897 | FY26: 2372467; FY27: 2372467 | 6344831 | 0
CVTA-0023 | Mayo Bridge Replacement | VDOT | 104888 |  | FY18 | FY27 | FY27 |  | 5945055 | 2264074 | 81790871 | 90000000 | 85000000 | 85000000 | [5 empty] | 0 | FY27: 5000000 | 5000000 | 0
CVTA-0024 | POV Richmond Marine Terminal Access Improvements at I-95/Bells Road | VDOT |  |  | FY25 |  |  |  | 2000000 |  |  | 2000000 | 0 |  |  | 2000000 |  |  |  | 2000000 | [7 empty] | 2000000 | 0
CVTA-0025 | RT 288 NB Flyover to Bailey Bridge Connector - PE ONLY |  |  |  | FY23 |  |  |  | 3696750 |  |  | 3696750 | 0 |  |  | 3696750 |  |  |  | 3696750 | [7 empty] | 3696750 | 0
CVTA-0026 | N. Gayton Road Interchange at I-64 |  |  |  | FY23 |  |  |  | 4985000 |  |  | 4985000 | 0 |  |  | 4985000 |  |  |  | 4985000 | [7 empty] | 4985000 | 0
CVTA-0027 | Chippenham Parkway/RT 60 Interchange Improvements |  |  |  | FY24 |  |  |  | 2000000 |  |  | 2000000 | 0 |  |  | 2000000 |  |  |  | 2000000 | [7 empty] | 2000000 | 0
CVTA-0028 | Rt. 301 3rd Southbound Lane | Local |  |  | FY22 | FY23 | FY24 | FY25 | 400000 | 52403 | 777455 | 1229858 | 400000 |  | 400000 |  |  | 52403 | 777455 | 829858 | [7 empty] | 829858 | 0
CVTA-0029 | W Broad Street Intersection Improvements at Parham Road |  |  |  | FY26 | FY31 | FY33 | FY34 | 1812725 | 3173102 | 10703943 | 15689770 | 0 | [6 empty] | 0 | FY26: 1812787; FY27: 1148225 | 2961012 | 12728758 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0030 | Rt. 1/Rt. 30 Green-T | Local |  |  | FY22 | FY24 | FY26 | FY26 | 600000 | 1514091 | 3440028 | 5554119 | 600000 |  | 600000 |  |  |  | 1514091 | 1514091 | FY26: 3440028 | 4954119 | 0
CVTA-0031 | A Hull Street Phase II (US360) |  | 121391 |  | FY26 | FY26 | FY27 | FY29 | 1012602 | 2834090 | 20019799 | 23866491 | 1000000 | 1000000 | [5 empty] | 0 | FY26: 993093; FY27: 2620765; FY28: 3553677; FY29: 4558767 | 11726302 | 11140189 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0032 | Rt. 301/Rt. 54 Roundabout | Local |  |  | FY24 | FY25 | FY27 | FY28 | 700000 | 905000 | 2919642 | 4524642 | 0 |  |  |  |  | 700000 | 905000 | 1605000 | FY26: 2919642 | 4524642 | 0
CVTA-0033 | W Broad Street Improvements - Short Pump |  |  |  | FY24 | FY27 | FY29 | FY30 | 2864430 | 1811551 | 21323989 | 25999970 | 22769970 | 22769970 |  |  |  | 3038850 |  | 3038850 | FY27: 191150 | 3230000 | 0
CVTA-0034 | I-95/Route 10 Interchange Improvement, Phase II |  |  |  | FY26 | FY29 | FY31 | FY33 | 3791955 | 1199725 | 50440357 | 55432037 | 0 |  |  |  |  | 750000 |  | 750000 | FY26: 1521043; FY27: 1521043; FY29: 1199748; FY30: 14422133 | 19413967 | 36018070 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment; SPA committed funds left in FY23
CVTA-0035 | Magellan Parkway Bridge and Approach Section |  |  |  | FY22 | FY23 | FY24 | FY26 | 2010000 | 1346000 | 15216000 | 18572000 | 0 |  |  |  | 2010000 | 1346000 | 6086400 | 9442400 | FY25: 6086400; FY26: 3043200 | 18572000 | 0
CVTA-0036 | G Broad Street Streetscape (US250) with Pulse Expansion Phase III |  |  |  | FY24 | FY27 | FY29 | FY30 | 2244280 | 3928349 | 17680107 | 23852736 | 15052736 | 15052736 |  |  |  | 2380938 |  | 2380938 | FY26: 2547668; FY27: 3871394 | 8800000 | 0
CVTA-0037 | Brook Road Improvements - Villa Park Dr to Hilliard Rd |  |  |  | FY23 | FY24 | FY25 | FY27 | 1305000 | 1799000 | 7312000 | 10416000 | 0 |  |  |  |  | 1305000 | 1799000 | 3104000 | FY25: 2508672; FY26: 2924800; FY27: 1878528 | 10416000 | 0
CVTA-0038 | Woolridge Road (Route 288 - Old Hundred Road) Extension |  | 112974 |  | FY19 | FY23 | FY24 | FY27 | 5000000 | 1000000 | 48252500 | 54252500 | 16674334 | 16674334 |  |  | 19578166 | 18000000 |  | 37578166 | [7 empty] | 37578166 | 0
CVTA-0039 | Staples Mill Road Improvements |  |  |  | FY24 | FY27 | FY30 | FY31 | 2708959 | 4522323 | 24904137 | 32135419 | 26465419 | 26465419 |  |  |  | 4331401 |  | 4331401 | FY27: 1338599 | 5670000 | 0
CVTA-0040 | Woodman Road Improvements - Mountain Rd to Hungary Rd |  |  |  | FY23 | FY24 | FY26 | FY27 | 3270000 | 18795570 | 40503738 | 62569308 | 0 |  |  |  |  | 3270000 | 9397785 | 12667785 | FY25: 6102121; FY26: 9078094 | 27848000 | 34721308
CVTA-0041 | Route 288 Southbound Hard Shoulder Running Lane | VDOT |  |  | FY26 | FY29 | FY31 | FY33 | 5949035 | 614164 | 55177426 | 61740625 | 0 | [6 empty] | 0 | FY26: 3662106; FY27: 1300000 | 4962106 | 56778519 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0042 | Route 360 (Woodlake Village Pkwy - Otterdale Rd) Widening |  |  |  | FY26 | FY29 | FY32 | FY33 | 3492669 | 8235557 | 28374998 | 40103224 | 0 |  |  |  |  | 750000 |  | 750000 |  | 1134765 | 1134765 | 9500000 | 10281546 | 10750000 |  | 33551076 | 6552148 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment; SPA committed funds left in FY23
CVTA-0043 | Vaughan Road Overpass | VDOT |  |  | FY26 | FY26 | FY28 | FY32 | 2868981 | 6875077 | 37458815 | 47202873 | 3568571 |  | 3568571 |  |  |  |  | 0 | FY26: 2673865; FY27: 2673865 | 5347730 | 38286572 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0044 | B Forest Hill Avenue Phase II |  |  |  | FY26 | FY29 | FY32 | FY33 | 3753086 | 10187873 | 32307254 | 46248213 | 0 | [6 empty] | 0 | FY26: 2917877; FY29: 11547247; FY30: 2211496 | 16676620 | 29571593 | Project start moved to FY26 start to match SSR6; total leverage inflated based on schedule adjustment
CVTA-0045 | I-64 Widening | VDOT |  |  | FY23 |  | FY25 |  |  |  |  | 522127470 | 422127470 | 422127470 | 0 |  | 16245833 | 11237395 | 25664649 | 53147877 | FY25: 28342043; FY26: 18510080 | 100000000 | 0
CVTA-0046 | D Hull Street Shared Use Path | Local | -27853 |  | FY26 | FY29 | FY31 | FY32 | 1520238 | 835393 | 9197461 | 11553092 | 8027213 | 8027213 | 0 |  |  |  |  | 0 | FY31: 3152729 | 3152729 | 373150
CVTA-0047 | E Richmond Highway Fall Line Trail Improvements | Local | 119598 |  | FY24 | FY25 | FY27 | FY29 | 3223800 | 1979775 | 34221316 | 39424891 | 16171265 | 16171265 | 0 |  |  |  |  | 0 | FY29: 5000000 | 5000000 | 18253626
CVTA-0048 | Busy Street Extension | Local | -28381 |  | FY26 | FY27 | FY28 | FY30 | 1439589 | 2361056 | 10535305 | 14335950 | 2018899 | 2018899 | 0 |  |  |  |  | 0 | FY27: 1781746; FY28: 1729404; FY29: 2000405 | 5511555 | 6805496
CVTA-0049 | Route 288 Southbound Auxiliary Lane | Local |  |  | FY26 | FY27 | FY28 | FY30 | 2591553 | 1856542 | 16152339 | 20600434 | 0 | 0 | 0 |  |  | 6167826 | 1332174 | 7500000 | [7 empty] | 7500000 | 13100434
CVTA-0050 | F Port of Virginia Gateway Interchange and Streetscape Improvements | Local |  |  | FY26 | FY30 | FY32 | FY33 | 2289716 | 7009393 | 15913502 | 25212611 | 0 | 0 | 0 |  |  |  | 2878344 | 2878344 | FY25: 119138; FY29: 1885564; FY30: 1803961; FY31: 1803994 | 8491001 | 16721610
CVTA-0051 | Route 250 at Route 288 Interchange Improvements | Local |  |  | FY26 | FY29 | FY31 | FY32 | 2878344 | 2798114 | 25152601 | 30829059 | 0 | 0 | 0 |  |  | 7500000 |  | 7500000 | [7 empty] | 7500000 | 23329059
CVTA-0052 | Route 60/33/Beulah Roundabout | Local | 118155 |  | FY24 | FY27 | FY29 | FY30 | 1400490 | 3758717 | 8707564 | 13866771 | 689000 | 689000 | 0 |  |  |  | 3000000 | 3000000 | [7 empty] | 3000000 | 10177771
CVTA-0053 | Route 60 (Village of Midlothian) Corridor Enhancements | Local |  |  | FY24 | FY26 | FY27 | FY28 | 3300435 | 3325592 | 31431710 | 38057737 | 2500000 | 0 | 2500000 |  |  |  | 800435 | 800435 | FY25: 4393738; FY27: 15625417; FY28: 32526 | 20852116 | 14705621
CVTA-0054 | I-64 Exit 211 Interchange Improvement Project | Local |  |  | FY26 | FY27 | FY27 | FY30 | 7414116 | 2160082 | 90023247 | 99597445 | 12000000 | 0 | 12000000 |  |  |  |  | 0 | 3500000 | 271619 | 3642497 | 3700000 | 5000000 | 2191034 |  | 18305150 | 69292295
CVTA-0055 | Powhite Parkway Extended, Phase I | Local |  |  | FY21 | FY26 | FY28 | FY30 | 10115937 | 18781978 | 201502458 | 230400373 | 170000000 | 0 | 170000000 |  |  |  |  | 0 | FY28: 3704277; FY29: 13795723; FY30: 9750000 | 27250000 | 33150373
CVTA-0056 | Rt. 360/Walnut Grove Rd Intersection Improvement | Local |  |  | FY28 | FY30 | FY32 | FY34 | 1295723 | 2271470 | 11059618 | 14626811 | 0 | 0 | 0 |  |  |  |  | 0 | FY28: 1295723; FY30: 2000000; FY31: 6704277 | 10000000 | 4626811
CVTA-0057 | Short Pump Area Improvements | Local |  |  | FY26 | FY28 | FY30 | FY32 | 27543758 | 7990503 | 325756193 | 361290454 | 0 | 0 | 0 |  |  |  |  | 0 | 10000000 |  | 10000000 |  | 7500000 | 5250000 | 27250000 | 60000000 | 301290454
CVTA-0058 | Rt. 5/New Osborne Turnpike Improvements | Local |  |  | FY25 |  |  |  | 4000000 | 0 | 0 | 4000000 | 0 | 0 | 0 |  |  | 4000000 |  | 4000000 | [7 empty] | 4000000 | 0
CVTA-0059 | Rt. 1 and Ashcake Intersection | VDOT |  |  | FY26 | FY28 | FY29 | FY29 | 981798 | 899956 | 3847280 | 5729034 | 50000 | 0 | 50000 |  |  |  | 2180340 | 2180340 | [7 empty] | 2180340 | 3498694
CVTA-0060 | US 60/VA13 Intersection Improvement | VDOT |  |  | FY26 | FY30 | FY31 | FY33 | 1576447 | 6150244 | 9962726 | 17689417 | 0 | 0 | 0 |  |  |  | 3042116 | 3042116 | FY25: 1957884 | 5000000 | 12689417
CVTA-0061 | Atlee Rd/Meadowbridge Rd Intersection Improvement | Local |  |  | FY25 |  |  |  | 750750 | 0 | 0 | 750750 | 0 | 0 | 0 | 234000 |  | 466000 |  | 700000 | [7 empty] | 700000 | 50750
CVTA-0062 | North South BRT | Local |  |  | FY25 | FY27 | FY29 | FY31 | 13928922 | 1973708 | 127608025 | 143510655 | 0 | 0 | 0 |  |  |  |  | 0 | FY31: 8000000 | 8000000 | 135510655
CVTA-0063 | Pulse Extension West (GRTC) | Local |  |  | FY24 | FY24 | FY27 | FY28 | 4578140 | 9060000 | 52996549 | 66634689 | 0 | 0 | 0 |  |  | 7000000 |  | 7000000 | [7 empty] | 7000000 | 59634689
CVTA-0064 | Downtown Transit Hub | Local |  |  | FY26 | FY27 | FY29 | FY31 | 2976750 | 3125520 | 34460100 | 40562370 | 0 | 0 | 0 |  |  |  |  | 0 | FY27: 10849; FY28: 6489151 | 6500000 | 34062370
SUBTOTAL | [11 empty] | 2748738440 | 962210122 | 768409551 | 193800571 | 47736311 | 71982846 | 77280000 | 71860000 | 268859157 | 67572000 | 68756500 | 67088000 | 65100000 | 62769000 | 59813000 | 60411000 | 720368657
| PROJECTED & ACTUAL REVENUE | [14 empty] | 47736311 | 71982846 | 77280000 | 71860000 | 268859157 | 73150000 | 76790000 | 79560000 | 82290000 | 84910000 | 87050000 | 87921000 | 840530157
| PROJECT ALLOCATIONS | [14 empty] | 47736311 | 71982846 | 77280000 | 71860000 | 268859157 | 67572000 | 68756500 | 67088000 | 65100000 | 62769000 | 59813000 | 60411000 | 720368657
| BALANCE ENTRY | [14 empty] | 0 | 0 | 0 | 0 | 0 | 5578000 | 8033500 | 12472000 | 17190000 | 22141000 | 27237000 | 27510000 | 120161500
| REMAINING FUNDS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | Actual | 7.625% | 10.46% | 15.68% | 20.89% | 26.08% | 31.29% | 31.29%
[20 empty] | Target | 10% | 15% | 20% | 25% | 30% | 35% | 35%
[20 empty] | Off-Cycle Funds | 5578000 | 354500 | 538000 | 732000 | 913500 | 1122000 | -3262350 | 5975650
MAB - Updated Projected Revenues based on 7/10 Finance Packet; adjusted balance entry to avoid impacts to project allocations; % in BE calculated below (in line with where it should be for FY26-FY31 allocation plan based on BE targets)